## Summary
IT Due Diligence Analysis Summary
Run ID: | RUN-7f94f0d9
Generated: | 2026-01-14 17:07
Run Name: | Project Atlas
Status: | completed
Findings Summary
Risks | 7
Gaps | 6
Work Items | 8
Recommendations | 4
Current State Items | 6
Assumptions | 1
Questions | 0
Risk Severity Breakdown
Critical | 0
High | 5
Medium | 2
Low | 0
Work Items by Phase
Day 1 | 2
Day 100 | 5
Post 100 | 1
Optional | 0

## Risks
# | Domain | Risk Description | Severity | Likelihood | Risk Type | Integration Dependent | Deal Impact | Mitigation | Cost Impact | Evidence Quote | Evidence Type | Confidence
1 | cross-domain | Platform architecture mismatch requiring dual-cloud operations during transition period | medium | high | integration | Yes | cost_exposure, execution_risk | Develop cloud rationalization strategy, negotiate AWS enterprise discount during transition, establish Azure migration factory | $500K-$1M in additional cloud and integration costs | AWS (Primary Cloud) - Monthly spend: ~$45,000 | direct_statement | high
2 | infrastructure | Cloud platform mismatch - target uses AWS as primary cloud while buyer environment is Azure-centric | medium | high | integration | Yes | execution_risk, cost_exposure, timeline_risk | Assess migration complexity, consider multi-cloud strategy, or maintain separate cloud environments | $300K-$800K | AWS (Primary Cloud) - Monthly spend: ~$45,000 | logical_inference | high
3 | cross-domain | Cross-domain dependency: Identity integration must complete before any application migrations can begin, as all systems rely on Active Directory authentication | high | high | integration | Yes |  | Identity integration (WI-007) must precede SAP migration and cloud platform rationalization work
4 | cross-domain | Cross-domain dependency: Network IP renumbering must complete before cloud migration to Azure can proceed due to address space conflicts | high | high | integration | Yes |  | IP renumbering (WI-003) must complete before AWS to Azure migration (WI-004) can begin
5 | cross-domain | Cross-domain dependency: Security baseline establishment required before any system migrations to ensure compliance and security posture | high | high | integration | Yes |  | Critical vulnerability remediation (WI-001) and EDR deployment (WI-003) must precede infrastructure migrations
6 | cross-domain | Cross-domain dependency: Key person retention program must execute before technical knowledge transfer initiatives to prevent knowledge loss | high | high | integration | Yes |  | Retention program (WI-001) must execute immediately, before SAP documentation (WI-002) and network cross-training (WI-006)
7 | cross-domain | Cumulative timeline risk from multiple long-lead critical path items creating 18-24 month integration timeline | high | high | integration | Yes | timeline_risk, cost_exposure, tsa_dependency | Negotiate minimum 18-month TSA with buyer, establish dedicated integration PMO, run parallel workstreams where possible | $2M-$4M in extended TSA and program costs | Colocation lease expires: March 2026 (18 months remaining) | direct_statement | high

## Gaps
# | Domain | Gap Description | Why Needed | Priority | Gap Type | Suggested Source | Cost Impact | Question Status
1 | applications | Workday HCM module deployment details and integration with other systems | Need to understand which Workday modules are deployed and how they integrate with other systems for consolidation planning | medium | incomplete_detail | Request Workday tenant configuration report and integration documentation | medium | not_asked
2 | applications | Salesforce CRM implementation details including version, edition, customization level, user count, and integration complexity | Critical for assessing integration complexity with buyer's CRM strategy and estimating consolidation or migration effort | high | incomplete_detail | Request Salesforce org assessment report including user licenses, custom objects, workflows, and integrations | medium | not_asked
3 | applications | Custom Manufacturing Execution System (MES) technical details including platform, vendor, version, customization level, and integration dependencies | MES is critical for manufacturing operations and integration complexity assessment. Need to understand replacement vs integration options | high | incomplete_detail | Request detailed MES system documentation including architecture diagrams, integration points, and vendor information | high | not_asked
4 | applications | Complete application inventory with business criticality ratings, user counts, licensing costs, and vendor contract terms | Required for comprehensive application rationalization, cost optimization, and integration planning decisions | high | missing_document | Request comprehensive application inventory spreadsheet or CMDB export with all business applications | high | not_asked
5 | applications | Application integration architecture documentation including data flows, APIs, middleware, and dependencies | Critical for understanding integration complexity, identifying single points of failure, and planning integration changes | high | missing_document | Request integration architecture diagrams, interface documentation, and data flow maps | medium | not_asked
6 | applications | Application licensing and vendor contract terms including change of control clauses and renewal dates | Critical for understanding deal impact on vendor relationships and potential cost increases or renegotiation requirements | high | missing_document | Request vendor contract summary with key terms, renewal dates, and change of control provisions | high | not_asked

## Work Items
# | Domain | Title | Description | Category | Phase | Phase Rationale | Effort Estimate | Cost Estimate | Skills Required | Dependencies | Triggered By
1 | applications | SAP Knowledge Transfer and Documentation | Immediate knowledge transfer from key SAP expert "Dave" including documentation of all custom ABAP programs, integrations, and business processes. Create comprehensive SAP system documentation and cross-train additional team members. | remediation | Day_1 | Critical risk mitigation to prevent loss of institutional knowledge for core ERP system. Must be completed immediately to ensure business continuity. | 12-16 weeks | $150K-$250K | sap_consultant, abap_developer, technical_writer, knowledge_management |  | R-002
2 | cross-domain | Integration Program Management Office Establishment | Establish dedicated PMO to coordinate cross-domain integration activities, manage dependencies, and provide executive reporting. Include dedicated program manager, integration architects, and coordination resources. | integration | Day_1 | PMO must be established immediately to coordinate all subsequent integration activities and manage complex dependencies | 6-12 months ongoing | $800K-$1.2M | program_manager, integration_architect, project_coordinator |  | R-005
3 | cybersecurity | Incident Response Plan Development | Develop comprehensive incident response plan including procedures, team roles, communication templates, and legal requirements. Conduct tabletop exercise to validate plan effectiveness. | security | Day_100 | Basic security preparedness requirement that can be developed quickly and provides immediate risk reduction | 3-4 weeks | $50K-$100K | security_consultant, legal_counsel, communications_specialist |  | R-006
4 | applications | AS/400 System Assessment and Modernization Planning | Assess AS/400 inventory system criticality, document functionality, identify replacement options, and develop modernization roadmap. Secure AS/400 specialist support for maintenance and transition planning. | assessment | Day_100 | System is currently functioning but needs assessment and planning for long-term viability. Not immediately critical but important for operational stability. | 8-12 weeks | $100K-$200K | as400_specialist, legacy_modernization_architect, business_analyst |  | R-003
5 | applications | SAP S/4HANA Readiness Assessment | Comprehensive assessment of SAP ECC 6.0 system for S/4HANA readiness including custom code analysis, data quality assessment, integration impact analysis, and migration planning. Evaluate cloud vs on-premise deployment options. | assessment | Day_100 | Critical for long-term ERP strategy but not immediately urgent. Assessment needed to plan for 2027 support deadline and inform integration decisions. | 16-20 weeks | $200K-$350K | sap_s4hana_architect, abap_developer, data_migration_specialist, integration_architect | WI-002 | R-001
6 | applications | Cloud Platform Rationalization Strategy | Develop strategy for consolidating AWS and Azure environments, including application migration assessment, cost-benefit analysis of dual-cloud vs single-cloud approach, and phased migration planning. | integration | Day_100 | Important for long-term cost optimization and operational simplicity, but not critical for immediate business continuity | 8-12 weeks | $100K-$175K | cloud_architect, migration_specialist, cost_analyst | WI-001 | R-005, SC-001
7 | applications | Application Integration Documentation | Document all existing application integrations including data flows, APIs, file transfers, and dependencies. Create integration architecture diagrams and establish change management processes for future modifications. | remediation | Day_100 | Critical for understanding integration complexity and enabling future changes, but not immediately blocking business operations | 10-14 weeks | $125K-$200K | integration_architect, technical_writer, business_analyst | WI-001 | R-004
8 | identity_access | Identity Integration with Buyer Environment | Establish federation or migration path between target's AD/Azure AD and buyer's Azure AD environment. Plan user migration, group consolidation, and application re-authentication. Implement cross-forest trusts if needed. | integration | Post_100 | Full integration requires careful planning and testing, builds on stabilized identity infrastructure | 12-20 weeks | $400K-$800K | iam_architect, azure_ad_specialist, migration_specialist | WI-001, WI-005 | R-005, SC-001

## Recommendations
# | Domain | Recommendation | Rationale | Priority | Timing | Investment Required | Driven By
1 | cybersecurity | Extend TSA for identity services during Azure AD migration | Complex identity migration from on-premises AD to Azure AD will require 12-18 months and careful planning to avoid business disruption | high | pre_close | $50K-$100K for extended TSA services | SC-004, R-009
2 | applications | Factor SAP S/4HANA migration costs into deal valuation as this is a mandatory upgrade regardless of integration strategy | SAP ECC 6.0 support ends in 2027, making S/4HANA upgrade unavoidable. Heavy customizations (150+ ABAP programs) will make this expensive and complex | high | pre_close | $2M-$5M+ for S/4HANA migration | R-001, SC-003
3 | applications | Conduct detailed application portfolio assessment immediately post-close to inform integration and rationalization decisions | Current documentation lacks critical details on application versions, customizations, and integrations needed for informed integration planning | high | day_1 | $75K-$125K for comprehensive assessment | CS-006
4 | applications | Prioritize immediate SAP knowledge transfer and documentation to mitigate critical key person risk | Single point of failure for core ERP system with 25-year expert and no documentation creates unacceptable business continuity risk | critical | pre_close | $150K-$250K for comprehensive knowledge transfer program | R-002

## Current State
# | Domain | Category | Item Name | Description | Status | Maturity | Standalone Viability | Key Characteristics
1 | applications | application_portfolio | Mixed application portfolio with modern cloud SaaS (M365, Workday, Salesforce), on-premise ERP (SAP ECC), and legacy systems (AS/400). No comprehensive application inventory or rationalization program | Mixed application portfolio with modern cloud SaaS (M365, Workday, Salesforce), on-premise ERP (SAP ECC), and legacy systems (AS/400). No comprehensive application inventory or rationalization program evident. | documented | medium | constrained | Mixed cloud and on-premise, Modern SaaS adoption, Legacy system dependencies, No formal portfolio management
2 | applications | collaboration_systems | Microsoft 365 E3 deployment with 1,100 mailboxes, SharePoint Online for documents, and Teams adoption at approximately 60%. Full cloud-based collaboration suite. | Microsoft 365 E3 deployment with 1,100 mailboxes, SharePoint Online for documents, and Teams adoption at approximately 60%. Full cloud-based collaboration suite. | documented | high | viable | Microsoft 365 E3, 1,100 mailboxes, SharePoint Online, 60% Teams adoption
3 | applications | crm_systems | Salesforce CRM platform deployed. No details provided on version, customization level, user count, or integration complexity. | Salesforce CRM platform deployed. No details provided on version, customization level, user count, or integration complexity. | documented | medium | viable | Salesforce platform, Details not specified
4 | applications | custom_applications | Custom manufacturing execution system (MES) and legacy AS/400 IBM i inventory system. The AS/400 system has no current maintenance expertise available. | Custom manufacturing execution system (MES) and legacy AS/400 IBM i inventory system. The AS/400 system has no current maintenance expertise available. | documented | low | high_risk | Custom MES system, Legacy AS/400 inventory system, No AS/400 maintenance expertise
5 | applications | erp_systems | SAP ECC 6.0 on-premise deployment with approximately 150 custom ABAP programs and heavy integration with manufacturing systems. No S/4HANA upgrade planned. System managed by single key person with 25 | SAP ECC 6.0 on-premise deployment with approximately 150 custom ABAP programs and heavy integration with manufacturing systems. No S/4HANA upgrade planned. System managed by single key person with 25 years experience. | documented | medium | constrained | On-premise deployment, 150+ custom ABAP programs, Heavy manufacturing integration, No upgrade path planned, Single person dependency
6 | applications | hcm_systems | Workday HCM platform implemented 2 years ago. Modern cloud-based HR system serving 1,200 employees across 5 locations. | Workday HCM platform implemented 2 years ago. Modern cloud-based HR system serving 1,200 employees across 5 locations. | documented | high | viable | Cloud-based Workday, Recently implemented (2 years), Serves 1,200 employees

## Assumptions
# | Domain | Assumption | Basis | Confidence | Impact | Validation Needed | Validation Status
1 | identity_access | Target company has approximately 1,200 user accounts in Active Directory matching employee count | Document states 1,200 employees and mentions Active Directory as primary identity system, typical for organizations to have 1:1 employee to user account ratio | medium | medium | Request Active Directory user count report including active/inactive accounts, service accounts, and contractor accounts | unvalidated